## Test Scenarios
Scenario Id | Test Scenario | No of test cases
S001 | Validate user access in DHPortal | 4
S002 | Validate circle packing updating | 3
S003 | Verify meta-data loading | 4
S004 | Validate data harmonization | 4
15

## Test Cases for S001
Scenario Id | Test Case Id | Test Case | Step | Step description | Expected Result | Actual Result | Status
S001 | C001 | Test 'Register' functionality with unregistered user data | Step 1 | Insert a username, e-mail and a password in the relevant fields. Click on 'Register' button. | A new user will be added in 'dh_users' database and the user will be transferred in the Home Page of the DHPortal. | A new recording is added in the 'users' table of 'dh_users' database and the user is transferred to the Home Page (home.php). | Pass
S001 | C002 | Test 'Register' functionality of an already registered user | Step 1 | Insert an already existing username, e-mail and a password in the relevant fields. Click on 'Register' button. | A pop up message informs the unregistered user that a user with the inserted data already exists. | An alert message shows up. | Pass
S001 | C003 | Test 'Log In' functionality with valid data | Step 1 | Insert an already existing username, e-mail and a password in the relevant fields. Click on 'Log in' button. | The user will be logged in and be transferred at the Home Page of DHPortal. | A session with the logged in user's name began and the Home Page (home.php) loaded. | Pass
S001 | C004 | Test 'Log In' functionality with invalid data | Step 1 | Insert a random username, e-mail and a password in the relevant fields. Click on 'Log in' button. | A pop up message informs the user that a wrong e-mail or password have been inserted. | An alert message shows up. | Pass

## Test Cases for S002
Scenario Id | Test Case Id | Test Case | Step | Step description | Expected Result | Actual Result | Status
S002 | C005 | Test circle update by adding new elements. | Step 1 | Create a plethora of groups with different codes,labels and parents as well. Click on 'Save' Button of the 'Selected Group' fieldset. | The circle packing on the upper left panel should be displayed and updated each time a new group is added. | The local JSON is updated each time a new group instance is saved and the circle packing is updated accordingly. | Pass
|  |  | Step 2 | Create a plethora of variables with different codes,labels and groups as well. Click on 'Save' Button of the 'Selected Variable fieldset. | The circle packing on the upper left panel should be displayed and updated each time a new variable is added. The variable table on the upper right panel should create a table with all these variables and their data. | The local JSON is updated each time a new variable instance is saved and the circle packing is updated accordingly. | Pass
S002 | C006 | Test circle update by editing new elements. | Step 1 | Click on a circle from the circle packing and edit a few variable data. Click 'Save' Button of the 'Selected Variable' fieldset. | The label of the visualized circle in the the circle packing should have the new label name. The variable table should be updated and the new data will replace the old ones. | The new data are shown on the variable table and the circle packing is updated accordingly. | Pass
|  |  | Step 2 | Click on a circle from the circle packing and edit a few group data. Click 'Save' Button of the 'Selected Group' fieldset. | The label of the visualized group in the the circle packing should have the new label name and the new parent (if it is changed). | The local JSON is updated each time a new group instance is saved and the circle packing is updated accordingly. | Pass
S002 | C007 | Test circle update by deleting new elements. | Step 1 | Click on a circle from the circle packing and delete any of the groups by clicking the 'Delete' Button of the 'Selected Group' fieldset. | The selected Group should be deleted from the circle packing. | The deleted circle doesn't exist in the circle packing and the JSON is updated. | Pass
|  |  | Step 2 | Click on a circle from the circle packing and delete any of the variables by clicking the 'Delete' Button of the 'Selected Variable' fieldset. | The selected variable should be deleted from the circle packing and the variable table. | The deleted circle doesn't exist in the circle packing and the JSON is updated. The variable is also deleted from the variable table. | Pass

## Test Cases for S003
Scenario Id | Test Case Id | Test Case | Step | Step description | Expected Result | Actual Result | Status
S003 | C008 | Test upload meta-data (JSON) from Local Space. | Step 1 | Click on 'Upload meta-data (JSON)' from the navigation menu. | Load local directories. | The default 'Download' local directory is loaded. | Pass
|  |  | Step 2 | Select a saved JSON file. | The JSON file should be loaded and the circle packing will be created on the upper left panel. The upper right panel contains the variables that the JSON file had stored. | The circle packign and the variables that were stored in the nested JSON are shown on the upper panels. | Pass
S003 | C009 | Test upload variables (CSV) from Local Space. | Step 1 | Click on 'Upload Variable (CSV)' from the navigation menu. | Load local directories. | The default 'Download' local directory is loaded. | Pass
|  |  | Step 2 | Select a valid saved CSV file. | The CSV file should be loaded and the variables will be added into the variable table and the 'Ungrouped' tab. | The ungrouped variables are saved into the variable table and are ready to be grouped. | Pass
S003 | C010 | Test loading data from Server. | Step 1 | Click on 'Load meta-data' from the navigation menu. Select either 'public' or 'private folder'. | A pop up window with all the json and csv files that are saved to server's public or private folder will be loaded. | A pop up window with files is shown. | Pass
|  |  | Step 2a | Select a JSON file. | The JSON file should be loaded and the circle packing will be created on the upper left panel. The upper right panel contains the variables that the JSON file had stored. | The circle packing and the variables that were stored in the nested JSON are shown on the upper panels. | Pass
|  |  | Step 2b | Select a CSV file. | The CSV file should be loaded and the variabled will be added into the variable table and the 'Ungrouped' tab. | The ungrouped variables are saved into the variable table and are ready to be grouped. | Pass
S003 | C011 | Test loading data from Friends. | Step 1 | Click on 'Friends' Tab from the navigation menu. | All the connected users that the logged in user has added should be added at 'My Community' fieldset. | The added users are shown at 'My Community' Fieldset. | Pass
|  |  | Step 2 | Click on a friend icon. | A pop up window with all public files that are saved from that friend will be loaded. | A pop up window with files is shown. | Pass
|  |  | Step 3a | Select a JSON file. | The JSON file should be loaded and the circle packing will be created on the upper left panel. The upper right panel contains the variables that the JSON file had stored. | The circle packing and the variables that were stored in the nested JSON are shown on the upper panels. | Pass
|  |  | Step 3b | Select a CSV file. | The CSV file should be loaded and the variabled will be added into the variable table and the 'Ungrouped' tab. | The ungrouped variables are saved into the variable table with a light blue background color and are ready to be grouped. | Pass

## Test Cases for S004
Scenario Id | Test Case Id | Test Case | Step | Step description | Expected Result | Actual Result | Status
S004 | C012 | Test CSV loading | Step 1 | Click on the 'Data Harmonization' Tab. | The harmonization page (harmonization.php) should be loaded. The circle packing is shown on the left side. | The Circle packing that has been created so far is shown in the left side. | Pass
|  |  | Step 2a | Click on 'Upload Variable (CSV)' from the navigation menu. | Load local directories. | The default 'Download' local directory is loaded. | Pass
|  |  | Step 2b | Click on 'Load Variables (CSV)' from the navigation menu. Select either the private or the public folder. | A pop up window with all the json and csv files that are saved to server's public or private folder will be loaded. | A pop up window with files is shown. | Pass
|  |  | Step 3a | Select a saved CSV file. | The CSV file should be loaded and the variables will be added at the table on the right side. All the cell options and textareas will be added next to each variable. | The table on the right side shows the variables in each line and empty cells that need to be complete. | Pass
|  |  | Step 3b | Select a saved CSV file. If a JSON file is selected an alert message will be shown, informing the user to choose another type. | The same as the Step 3a of the C013 Test Case. | The same as the Step 3a of the C013 Test Case. | Pass
S004 | C013 | Test harmonized CSV | Step 1 | Load a CSV File. | Follow the Steps 1 - 3 of C012 Test Case. | The same as the Steps 1 - 3 of C012 Test Case. | Pass
|  |  | Step 2 | Select old variables to be macthed with the new ones select a function and insert data to any of the other textareas. | The data will be shown at the table. Whenever a function name is selected from the 'Using the Function(s)' its function will be added to 'Transform' textarea. | The data are correctly shown at the table. | Pass
|  |  | Step 3 | Click on 'Save Variables (CSV)' and then choose the Private or Public Folder. | The data will be saved as a CSV file on Server. | The functions that are chosen for each variable will be transformed according to a standard, and the CSV will be saved in the Server public or private folder. | Pass